## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 识别各种字体 | 作为一个经理，我希望能够不只是识别标准的汉字而是可以识别各种字体，以便于拓宽使用范围。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 联想功能友好 | 作为一个使用者，我希望可以正确预测我接下来要输入的汉字，以便于节约时间和方便操作。 | Initial Feature | Not Done | 1 | 96 |  |  | 1 | 0
3 | 1 | 1 | user story | 上传文件或直接书写 | 作为用户，我希望既可以传入图片又可以直接在手写板进行书写，以便于适用不同需求。 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 用户界面友好 | 作为用户，我希望用户界面布局合理，以便于在使用时可以操作简单。 | Initial Feature | Not Done | 1 | 93 |  |  | 1 | 0
5 | 1 | 1 | user story | 单写或连写 | 作为一个用户，我希望手写时可以输入一个字也可以输入一句话，以便于方便操作。 | Initial Feature | Not Done | 1 | 93 |  |  | 2 | 0
6 | 1 | 1 | user story | 查看历史 | 作为一个用户，我希望能够查看历史，以便于记录自己的使用情况。 | Initial Feature | Not Done | 0.5 | 80 |  |  | 1 | 0
7 | 1 | 1 | user story | 读音提示 | 作为用户，我希望识别出汉字的同时，可以对汉字进行拼音标注，以便于正确理解汉字。 | Initial Feature | Not Done | 2 | 80 |  |  | 2 | 0
8 | 1 | 1 | user story | 识别方言 | 作为产品经理，我希望程序可以识别各种方言，以便于提升用户好感度。 | Initial Feature | Not Done | 3 | 80 |  |  | 3 | 0
9 | 1 | 1 | user story | 自定义画笔 | 作为一个使用者，我希望能够自己设置画笔颜色、大小等，以便于符合自己的书写习惯。 | Initial Feature | Not Done | 0.5 | 85 |  |  | 1 | 0
10 | 1 | 1 | user story | 自定义背景 | 作为一个使用者，我希望能够自己设置输入法背景，以便于提升美感。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information